## Sheet1
TASK | Assigned to | Progress | 2020-09-21 | 2020-09-28 | 2020-10-05 | 2020-10-12 | 2020-10-19 | 2020-10-26 | 2020-11-02 | 2020-11-09 | 2020-11-16 | 2020-11-23 | 2020-11-30 | 2020-12-07 | 2020-12-14 | 2020-12-21 | 2020-12-28 | 2021-01-04 | 2021-01-11 | 2021-01-18 | 2021-01-25 | 2021-02-01 | 2021-02-08 | 2021-02-15 | 2021-02-22 | 2021-03-01 | 2021-03-08 | 2021-03-15 | 2021-03-22 | 2021-03-29 | 2021-04-05 | 2021-04-12 | 2021-04-19 | 2021-04-26 | 2021-05-03 | 2021-05-10
GANTT CHART | Al | 50% | bar: 2020-09-21 to 2020-09-28
Trade studies
Power stage | ALEX | 0% | bar: 2020-09-21 to 2020-10-05
Microcontroller | RICE | 0% | bar: 2020-09-21 to 2020-10-12
User Interface | AL | 0% | bar: 2020-09-21 to 2020-10-12
Standards Research | CHASE | 0% | bar: 2020-09-21 to 2020-10-12
Project Description | Al | bar: 2020-10-19
Technical Approach | Alex & Chase | bar: 2020-10-19
Power stage | Alex | bar: 2020-10-12
Microcontroller | Rice | 50% | bar: 2020-10-12
Display | Al | bar: 2020-10-12
Standards | Chase | bar: 2020-10-12
Management Approach | Rice | bar: 2020-10-19
Budget
Timeline | Al | 45% | bar: 2020-09-21; 2020-10-19
Facilities | Rice | bar: 2020-10-19
Dispositon | ALL | bar: 2020-10-26
Color Key
Goal
Revised
Incomplete